## Assignments
Project | Project API External Id | Resource | Resource API External Id | Task | Data Input | Plan Type | Allocation Type | Time Period | Import Behavior | Id | Action | Project Allocation | Priority | Complete | 2026-01-01 00:00:00 | 2026-02-01 00:00:00 | 2026-03-01 00:00:00 | 2026-04-01 00:00:00 | 2026-05-01 00:00:00 | 2026-06-01 00:00:00 | 2026-07-01 00:00:00 | 2026-08-01 00:00:00 | 2026-09-01 00:00:00 | 2026-10-01 00:00:00 | 2026-11-01 00:00:00 | 2026-12-01 00:00:00
Blockbuster App 2026 | stern-blockbuster-app-2026 | Brad Pitt | stern-brad-pitt | Generic | Hours | Planned | Planned | Month | [6 empty] | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160
Blockbuster App 2026 | stern-blockbuster-app-2026 | Meryl Streep | stern-meryl-streep | Generic | Hours | Planned | Planned | Month | [6 empty] | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160
Social Media Relaunch | stern-social-media-relaunch | Taylor Swift | stern-taylor-swift | Generic | Hours | Planned | Planned | Month | [6 empty] | 0 | 0 | 80 | 80 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0
Cloud Migration | stern-cloud-migration | Dwayne Johnson | stern-dwayne-johnson | Generic | Hours | Planned | Planned | Month | [6 empty] | 0 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 0 | 0 | 0 | 0
Compliance Update Q2 | stern-compliance-update-q2 | Angela Merkel | stern-angela-merkel | Generic | Hours | Planned | Planned | Month | [6 empty] | 0 | 0 | 0 | 120 | 120 | 120 | 0 | 0 | 0 | 0 | 0 | 0
Cloud Migration | stern-cloud-migration | Roger Federer | stern-roger-federer | Generic | Hours | Planned | Planned | Month | [6 empty] | 0 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 0 | 0 | 0 | 0
Blockbuster App 2026 | stern-blockbuster-app-2026 | Heidi Klum | stern-heidi-klum | Generic | Hours | Planned | Planned | Month | [6 empty] | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Blockbuster App 2026 | stern-blockbuster-app-2026 | Elon Musk | stern-elon-musk | Generic | Hours | Planned | Planned | Month | [6 empty] | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120
Innovation Sprint April-Mai | stern-innovation-sprint-apr-mai | Elon Musk | stern-elon-musk | Generic | Hours | Planned | Planned | Month | [6 empty] | 0 | 0 | 0 | 120 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0