Project Manager Guide

Created for

Knauf SE GmbH

Contents

Overview	3

Common Tempus Shortcuts	4

Tempus Resource Navigation	5

Logging In	5

Homepage	5

How to Subscribe to Notifications	7

Project Management GRId	8

How to Create a Project	8

Creating a project without a template	8

Creating a project with a template	9

View Management	10

How to Update Project Attributes	11

Editing Attributes for a Single Project	11

Editing Attributes for Multiple Projects	11

SINGLE PROJECT ALLOCATION GRID	12

Grid Overview	12

How to Assign Resources to Projects	13

Replacing a Resource	15

Resource Replace Screen	15

Fully or Partially Replacing a Resource	16

Advanced Assignment Options	17

Cloning an Assignment	17

Shifting an Assignment	17

Bulk Project Allocation Flatgrid	18

Grid Overview	18

How to Create a Multi-Project View	20

Actions in the BPA Flatgrid	22

Updating existing assignments	22

Adding new assignments	22

Replacing a Resource (Resource Replace Advanced)	23

# Overview

Planner scope (Knauf Phase 1): PM/SM and blended PM/SM + PPM are in scope. Resource Manager chapters (Bulk Project Allocation Flatgrid and enterprise-wide replace flows) ship separately.

- User Access:

Tempus access will vary based on the setup of each individual user (managed by your Admin team)

Resources who require access can login via SSO and will be assigned a user role and security group

- Resource Types:

There are two types of resources that can be setup in Tempus

  - Named resources: Individuals allocated to projects and/or setup as Tempus users

  - Group resources: Resources with underlying capacity for multiple resources e.g., Demand-planning generics

  - Demand Planning resources: Unnamed resources; generic placeholders for a team or role, used solely for planning

- Project Types:

There are three types of projects setup in your Tempus instance

- Standard projects: “Interrelated tasks organized together in order to reach a specific outcome”

- Proposals: Projects still pending approval, denoted by a purple P icon

- Non-Project Activities or Business As Usual projects: Absence, Admin, Run, Change, etc.

- Assignments

Assignments are created by linking a Resource to a Project

    - Assignments must include a specific number of time units (Hours, FTE, etc.)

    - Assignments can be created for one project at a time, or for multiple projects at the same time

    - Assignments can be applied to the Project (generic task) or to individual named tasks

# Common Tempus Shortcuts

- Tempus grids support the following Excel-like functionality:

  - Column data can be sorted by clicking the column header

  - Cell data can be copy-pasted via CTRL+C and CTRL+V

  - Cell data can be copied across or down by clicking the bottom-right corner of a cell and dragged along

- Tempus use several icons (across multiple screens) to represent specific functionality:

Trash Can:	Delete selected item(s)

Pencil:		Edit/View selected item

Copy/Clone:	Copy selected item to clipboard OR Clone selected item

Lock/Unlock:	Indicates whether the selected record is locked by another user

Export To:	Standard icons for Excel, CSV, or PDF display when applicable

Filter:		Filter results based on specified values

Notification:	Listed item may need attention (filters, new requests, etc.)

Listed record is a Demand Planning resource (generic, placeholder)

Listed record is a Proposal

# Tempus Resource Navigation

Tempus Resource is an easy to use resource management and workforce capacity planning tool with an intuitive user interface. This section covers the three aspects of navigating Tempus – Logging In, different areas of the Homepage and Main Task Bar, and Subscribing to notifications.

## Logging In

- Navigate to Tempus Resource using your web browser (https://knaufdev.tempus-resource.com/)https://knaufdev.tempus-resource.com/

Google Chrome is the recommended browser.

- Click on the orange button Knauf SSO

- Sign in using your standard credentials

## Homepage

      - Planner roles (PM/SM and blended PM/SM + PPM) see the homepage tiles provisioned for them — typically Project Management and Report Management. Click on any tile to navigate to the relevant area.

      - The below table provides a high-level description of actions users can perform behind each tile.

Note: The actions may vary depending on each user’s role and access permissions.

| Tile name* | Description |
| --- | --- |
| Project Management | View project repository ¦ Create projects with / without template ¦ Open projects ¦ Maintain allocations on the SPA grid |
| Report Management | Consume shared reports ¦ Export to Excel / PDF where licensed |

*Highlighted screenshots mirror Knauf Planner onboarding (PM/SM). RM-only surfaces such as Bulk Project Allocation are intentionally omitted from this edition.

      - The blue ribbon along the top (Task Bar) is available from all screens in Tempus.

- Click on the Tempus logo to the left to return to the homepage from any screen

- View notifications by clicking on the bell icon

- Locate a specific project via Global Search

- Navigate to any area of Tempus via the hamburger menu

- From the username menu, set up in-app Subscriptions or Logout.

## How to Subscribe to Notifications

- From the username menu to the top-right, click on Subscriptions.

- In the Project tab, click Add projects to choose projects to be notified for. Click the green Add button. NOTE: Do not select all projects as unsubscribing must be done individually.

As a default, all notifications will be enabled for selected projects.

- To disable a specific notification,

  - Hover over the cell

  - Click the Edit icon

  - Update Yes to No

  - Click the green Save button.

- To update notifications in bulk, follow the same steps as above while selecting multiple cells; by holding down the Shift Key on your keyboard and select multiple cells using arrow keys.

- To unsubscribe from a project, click

# Project Management Grid

Click the Project Management tile to open the Project List, where you have access to the entire project repository.

## How to Create a Project

Giving users the ability to create new projects and their tasks within the product is a core component of Tempus Resource. This section outlines how to create a project both with and without a template.

### Creating a project without a template

- Click on the green Create Project button towards the top-left of your Project Management grid and select Regular Project from the very top of the list.

- You will automatically land on the Project Allocations screen, where you can enter a Project Name, Start Date, and End Date

- Click the green Create button to the right of the Project Name to save the new project to your repository.

### Creating a project with a template

- Click on the green Create Project button towards the top-left of your Project Management grid and select the relevant template from the list.

- Clicking the template will open a modal window in the middle of your screen.

Enter the new Project’s name and click Create to save the new project to your repository.

- You will automatically land on the Project Allocations screen. Navigate to Project Attributes from the top-right of the screen.

- To update the project timeframe from the template values, click Shift, enter the New start date,

- Review and update all relevant attributes. Ensure that updates are saved by clicking on the green Save button at the very top of the screen.

## How to Update Project Attributes

Project attributes can be updated directly from the Project Management grid, both on an individual-level and in bulk.

### Editing Attributes for a Single Project

- Hover over the cell. An edit icon will appear to the right of the cell.

- Click the edit icon, choose the new value and click the green check mark icon. Alternatively, press Enter on your keyboard.

### Editing Attributes for Multiple Projects

- Select projects by checking boxes to the left of project names. Selected rows will be highlighted.

- To select a range of rows, select the row at the start of the range from the checkbox.

Press the Shift key on your keyboard and select the last row in the range. All rows will be highlighted.

- Hover over any cell from selected rows. The edit icon will appear to the right of the cell.

- Click the edit icon, choose the new value, and click the green check mark icon to update the value for all selected projects.

# SINGLE PROJECT ALLOCATION GRID

The Single Project Allocation (SPA) grid is where allocations to a single project can be created or updated.

- Clicking on any project name in the grid will navigate to the Single Project Allocation grid by default.

- Once a project has been created, and a valid date range has been entered, the Single Project Allocation grid becomes available.

## Grid Overview

      - The Project Name and Checkout button is located at the top of the grid.

To make any changes to a project, it must first be checked out.

      - Basic options to update the grid are in the ribbon below the project start and end date.

- Expand the grid with one-click by clicking on

- Search for an assigned resource when the grid is grouped by Resource and for a task name when the grid is grouped by Task.

- Group by either Resource or Task.

- Insert Columns to view project, resource, or assignment attributes.

- Update Time Granularity by which allocations are displayed. Month is the recommended granularity for Knauf.

- Choose the Capacity unit in which allocations are entered/displayed.

Hours are recommended for Knauf capacity planning (switch to Mandays when steering leadership).

      - Advanced grid options can be found in the Options menu in the ribbon below the project timeframe.

- Enabling the Total Column will display a column with total Hours.

When viewing the grid in FTE, it will display the average.

- A Resource Heatmap will display colours based on overall allocation% of a resource.

- Enabling Overlay Heatmap for Rows will apply the selected heatmap on individual grid rows.

- Enabling Overlay Heatmap for Groups will apply the selected heatmap on groupings.

- Tasks to Show will filter tasks and hide the task type that is not selected – generic or non-generic.

- The Date Range Filter will filter the grid for a specific timeframe without amending project timeframe.

## How to Assign Resources to Projects

- Click Checkout next to the Project Name at the top to make any edits to the project.

- Expand the grid by clicking on the button with 2 arrows  above the Name column in the grid.

- To add a single resource, click on a blue cell reading Type a new resource to start typing the name of the resource or select a resource from the dropdown.

Type-ahead functionality narrows down the available resources to simplify resource loading.

- To add multiple resources to one or multiple tasks, click on Add assignment to reveal the New Assignment dialog. Choose resources to the left and tasks to the right and click Add.

- To create a new task, scroll down to the end of the Task list to reveal a green row with the option to Type a new Task. Enter the name of the new task and hit enter or click the checkmark to the right of the cell.

- Enter the allocation in Hours on a monthly level. Values can be copy-pasted or clicked and dragged.

- To increase the allocated time for a named resource that has already been allocated to a project, enter the new total requested allocation directly in the grid.

- To save changes, click Save and Check In or Release them to revert to the previous state.

## Replacing a Resource

There are two cases when a resource needs to be replaced in a project –

- A Demand Planning or Placeholder resource needs to be replaced with a named individual e.g., *Project Manager (RBK) needs to be replaced with another named resource.

- A named resource needs to be replaced with another member of the resource pool e.g., another named resource needs to be replaced with Antonio Gonzalez on a given project.

To replace a resource, click on the ellipses next to the resource name to access the Resource Replace screen.

### Resource Replace Screen

- The top of half of the screen displays the current allocation in a grid with the option to update the time granularity (Month/Quarter/Year/Week/Day) and capacity unit (FTE/Hours).

- The bottom half displays all resources in the resource pool in a Net Availability grid to manually query and find the best fit resource by applying filters, inserting columns, or applying a simple red/green heatmap from the Options menu.

### Fully or Partially Replacing a Resource

- Select replacement resource(s) from the bottom of the grid and they will automatically appear in the allocation grid above.

- To fully replace a resource, click Redistribute to copy the complete allocation from the original resource to the replacement resource(s). If multiple resources are selected, the original allocation will be equally redistributed among them.

  - To partially replace the resource, update allocations directly in the grid ensuring that the Total row displays as green.

  - Click Replace at the top of the screen to complete the step.

## Advanced Assignment Options

Click on the ellipses next to the assignment name to access Assignment Options.

### Cloning an Assignment

- To Clone an assignment,

  - Enter the Task name,

  - Add a New assignment start date,

  - If changing the resource, toggle on the option and select the new resource’s name,

  - Click the green Apply button to save changes.

### Shifting an Assignment

- To Shift an assignment

  - Click on Shift,

  - Enter a New Assignment Start Date,

  - Click the green Apply button to save changes.

# PROJECT FINANCIALS

- Financial planning completes the Planner triangle together with Attributes and the Single Project Allocation grid. Hourly / Advanced rates are administered by Finance; PM/SM maintain Cost Plan overrides where permitted and interpret Budget vs Actual.

## Rates — Hourly & Advanced

- Hourly Rate — blended €/h per named or generic resource for a validity window; shown as read-only context while planning.

- Advanced Rate — dated brackets or uplifts (e.g. vendors). Tempus resolves the effective €/h per period; reconcile surprises via the SPA grid Cost view.

## Cost Plan & Budget vs Actual

- Cost Plan — derived from Hours × effective rate; Finance-approved manual cells capture non-hour spend (licences, PO-driven costs).

- Budget vs Actual — compares planned cost with booked hours × rate. Align granularity (month / quarter / year) with Knauf steering cadence.

## Lock Periods & Re-forecast

- Lock Periods — closed financial buckets prevent silent retro-edits; escalate hard-lock changes through PMO / Finance.

- Re-forecast — refresh forward buckets after actuals land; prefer SPA edits first so mandays / euros remain coherent before overriding Cost Plan cells.

## View Management

- Towards the top-right of the grid, there are various options to customise the Project management grid.

    - Use Quick filters to navigate to relevant projects e.g., “my projects” will show projects where the logged in user is assigned as the Project Owner.

    - Search for a project or projects by name via the search field, which uses “contains” logic.

    - Filter projects by applying as many filters as needed.

    - Add or remove Columns.

    - Group projects based on any attribute(s). Each grouping level will display the group by attribute, attribute value, and the count of projects contained in the grouping.

- Open the View Management dialog by clicking on the view name to the right of the Group By button.

| - Create a new view by clicking Create view - Lock a view in its current state by clicking - Select a Default view by clicking - Edit a view by clicking - Clone a view by clicking - Delete a view altogether by clicking |  |
| --- | --- |

- Public views are denoted by the blue eye shaped icon

These views cannot be edited in any way as they are administratively defined.

Always clone a public view using the copy icon , and then click into the newly created view to start working into it.