## Assignments
Project | Project API External Id | Resource | Resource API External Id | Task | Data Input | Plan Type | Allocation Type | Time Period | Import Behavior | Id | Action | Project Allocation | Priority | Complete | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01
Project A |  | Shelly Smith |  | Develop Documents | Hours | Allocation | Plan | Month | Merge |  |  |  | High | Yes | 2026-01-01: 45; 2026-02-01: 45; 2026-03-01: 45; 2026-04-01: 45; 2026-05-01: 45
Project A |  | Mike Scott |  | Develop Documents | Hours | Allocation | Plan | Month | Merge |  |  |  | High | No | 2026-01-01: 65; 2026-02-01: 65; 2026-03-01: 65; 2026-04-01: 65; 2026-05-01: 65
Project A |  | Mike Scott |  | Architecture Review | Hours | Allocation | Plan | Month | Merge |  |  |  | Low | No | 2026-04-01: 80; 2026-05-01: 80; 2026-06-01: 80; 2026-07-01: 150; 2026-08-01: 150; 2026-09-01: 120; 2026-10-01: 120
Project A |  | Shelly Smith |  | Architecture Review | FTE | Allocation | Plan | Month | Merge |  |  |  | Low | No |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.25
Project A |  | Shelly Smith |  | Develop Documents | Hours | Demand | Actual | Month | Merge |  |  |  | Medium | Yes | 2026-01-01: 20; 2026-02-01: 25; 2026-03-01: 25
Project A |  | Mike Scott |  | Develop Documents | Hours | Demand | Actual | Month | Merge |  |  |  | Medium | Yes | 2026-01-01: 30; 2026-02-01: 30; 2026-04-01: 30
Project A |  | Mike Scott |  | Architecture Review | Hours | Demand | Actual | Month | Merge |  |  |  | Low | No |  |  |  | 35 | 35 | 35 | 60 | 60 | 60 | 60 | 60 | 60
Project A |  | Shelly Smith |  | Architecture Review | FTE | Demand | Actual | Month | Merge |  |  |  | Medium | No |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.25
Project A |  | Megan Keller |  | Architecture Review | FTE | Demand | Actual | Month | Overwrite |  |  |  | Medium | No |  |  |  | 2 | 2 | 2 | 1.75 | 1.5 | 1.5 | 1 | 1 | 1
Project A |  | Megan Keller |  | Architecture Review |  | Allocation |  |  | Merge |  | Delete

## INSTRUCTIONS
Importing Assignment Data
Use the Excel import to add assignments and planned and actual values to projects. Add assignments at the project level using the ‘Generic’ task or add distinct tasks to projects. Import allocation and/or demand data by month, week or day by hours or by FTE. Update assignment attributes and – if needed – clear assignment data from Tempus.
There are two units available for import:
|  | Hours | Hours of effort which can be set by day, week, month or year using the import file.
|  | FTE | The fractional value of a resource's capacity allocated by day, week, month or year using the import file.
Two dataset options are available:
While the Allocation and Demand datasets can be renamed in Tempus, when using the Excel import, the intrinsic values of 'Allocation' and 'Demand' must be used.
|  | Allocation | The default, time-phased, standard, dataset for Tempus users. Includes planned and actual data.
|  | Demand | A secondary, time-phased, dataset available for more complex use cases. Includes planned and actual data.
Two dataset types are available:
|  | Planned | The planned allocation or planned demand data.
|  | Actual | The actual allocation or actual demand data.
Five time period options are available for Time Period:
The required assignment columns must match the 'Time Period' value
|  | Project | Dates are not required and ignored if specified. Project Allocation column is required. If you are importing hours, the hours will be spread over the working days in the project. If you are importing FTE, the FTE value will be replicated across all working days in the project.
|  | Year | Define any date within the year. If you are importing hours, the hours will be spread over the working days in the year. If you are importing FTE, the FTE value will be replicated across all working days in the year.
|  | Quarter | Define any date within the quarter. If you are importing hours, the hours will be spread over the working days in the quarter. If you are importing FTE, the FTE value will be replicated across all working days in the quarter.
|  | Month | Define any date within the month. If you are importing hours, the hours will be spread over the working days in the month. If you are importing FTE, the FTE value will be replicated across all working days in the month.
|  | Week | All dates must be the first Monday of the week. If you are importing hours, the hours for the week will be spread over the working days in the week. If you are importing FTE, the FTE value will be replicated across all working days in the week.
|  | Day | Dates must be continuous without gaps. Saturdays and Sundays must be included. However, please be aware that any values entered on Saturdays and/or Sundays will be skipped.
The import supports three behaviors:
You must define the behavior for each assignment under Import Behavior.
|  | Merge | If a assignment doesn’t exist, the Merge option will create the new assignment. If an assignment does exist, the Merge option will update the resource. Uniqueness is based on the project name, resource name, task name, plan type and allocation type.
|  | Overwrite | This option overwrites existing assignments where the project name, resource name, task name, plan type and allocation type match. Use this option when you wish to remove and replace an assignment.
|  | Skip | This option skips the entire row and no assignment information will be imported to Tempus.
Required Columns:
|  | Project | The name of the Project in which the assignment exists. Project Name must be used.
|  | Resource | The resource assigned. Resource Name must be used.
|  | Task | The name of the task. If the assignment is project-level, use the built in 'Generic' value.
|  | Data Input | Planned and actual assignment data can be imported as Hours or FTE.
|  | Plan Type | Input the dataset. The options are Allocation and Demand.
|  | Allocation Type | Within the selected dataset, select the series. The options are Plan and Actual.
|  | Time Period | Enter Project, Year, Quarter, Month, Week or Day. The value entered here must match the assignment data columns.
|  | Import Behavior | Select from the available import options of Merge, Overwrite, or Skip. Merge is recommended.
Optional User Definition Columns:
|  | Id | When the Allow Multiple Assignments option is switched on, you must define an assignment ID to update or delete the existing assignment. Rows with a blank ID will be imported as new assignments. If Allow Multiple Assignments is turned off, the value is optional and the assignment for the specified task and resource will be updated.
|  | Project API External Id | This value is ONLY required if you have configured Tempus to use API External ID as the primary key for the import in general settings.
|  | Resource API External Id | This value is ONLY required if you have configured Tempus to use API External ID as the primary key for the import in general settings.
|  | Action | The assignment import file contains an additional column for conducting special actions against assignments. The available option for the 'Action' column is "Delete." Adding this value, will clear the record from Tempus. When using this option, 'Data Input', 'Allocation Type', 'Time Period', and time-phased assignment data do not need to be provided.
|  | Project Allocation | Define the Hours or FTE for total project duration in this column. The column is required if Time Period is set to Project and ignored otherwise.
Optional Custom Attribute Columns:
Custom Assignment Attributes can be added to the assignment import template. Two sample assignment custom attributes are included. Remove these fields prior to import. Replace with your assignment custom attributes. Add as many columns as necessary. The assignment custom attributes must exist in order for the values to be imported. If the assignment custom attributes do not exist, the values will be skipped.
|  | Priority | A sample custom assignment attribute.
|  | Complete | A sample custom assignment attribute.
Assignment Data:
The assignment import file contains a sample time range. Modify this time range to match the 'Time Period' value and the timeframe you wish to update.
|  | 2022-01-01 | 2022-02-01 | 2022-03-01
How to import:
Complete the import template and the required fields.
Make sure the template is the first tab in the file.
Log into Tempus and go to Admin Settings > Data Synchronization > Excel.
Click Choose File and select your assignment import file or drag your file on to the page. The required file type is .xlsx
Click Synchronize.