## Assignments
Project | Project API External Id | Resource | Resource API External Id | Task | Data Input | Plan Type | Allocation Type | Time Period | Import Behavior | Id | Action | Project Allocation | Priority | Complete | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Manuel |  | PREPARE · Unterzeichnung Vertrag | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Giacomo Telesca |  | PREPARE · Unterzeichnung Vertrag | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Manuel |  | PREPARE · Salesübergabe | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Giacomo Telesca |  | PREPARE · Salesübergabe | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Manuel |  | PREPARE · Pre Kickoff | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Giacomo Telesca |  | PREPARE · Pre Kickoff | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Manuel |  | PREPARE · Tempus & Time · Kick-Off | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Giacomo Telesca |  | PREPARE · Tempus & Time · Kick-Off | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Manuel |  | PREPARE · Fachworkshop DM | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Giacomo Telesca |  | PREPARE · Fachworkshop DM | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Manuel |  | PREPARE · Abgabe finale Registerstruktur | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Giacomo Telesca |  | PREPARE · Abgabe finale Registerstruktur | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Manuel |  | PREPARE · Fachworkshop IT | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Giacomo Telesca |  | PREPARE · Fachworkshop IT | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Manuel |  | EXPLORE · Workshop Document Manager | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Giacomo Telesca |  | EXPLORE · Workshop Document Manager | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Manuel |  | EXPLORE · DM Testing Registerstruktur / Rollen | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Giacomo Telesca |  | EXPLORE · DM Testing Registerstruktur / Rollen | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Manuel |  | EXPLORE · Workshop Doc Generation I (Basics) | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Giacomo Telesca |  | EXPLORE · Workshop Doc Generation I (Basics) | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Manuel |  | EXPLORE · Workshop Doc Generation II (Advanced) | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Giacomo Telesca |  | EXPLORE · Workshop Doc Generation II (Advanced) | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Manuel |  | EXPLORE · Workshop e-Signature | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Giacomo Telesca |  | EXPLORE · Workshop e-Signature | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Manuel |  | REALIZE · Konfiguration Staging | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Giacomo Telesca |  | REALIZE · Konfiguration Staging | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Manuel |  | REALIZE · Konfiguration Staging Schnittstelle | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Giacomo Telesca |  | REALIZE · Konfiguration Staging Schnittstelle | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Manuel |  | REALIZE · Konfiguration Staging SSO | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Giacomo Telesca |  | REALIZE · Konfiguration Staging SSO | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Manuel |  | REALIZE · Konfiguration E-Signature | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Giacomo Telesca |  | REALIZE · Konfiguration E-Signature | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Manuel |  | REALIZE · Testing Staging DM | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Giacomo Telesca |  | REALIZE · Testing Staging DM | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Manuel |  | REALIZE · Testing Staging: SSO | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Giacomo Telesca |  | REALIZE · Testing Staging: SSO | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Manuel |  | REALIZE · Testing Staging: Stammdaten | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Giacomo Telesca |  | REALIZE · Testing Staging: Stammdaten | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Manuel |  | REALIZE · Abnahme Staging DM | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Giacomo Telesca |  | REALIZE · Abnahme Staging DM | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Manuel |  | DEPLOY · Konfiguration Prod | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Giacomo Telesca |  | DEPLOY · Konfiguration Prod | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Manuel |  | DEPLOY · Konfigration Prod: SSO | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Giacomo Telesca |  | DEPLOY · Konfigration Prod: SSO | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Manuel |  | DEPLOY · Testing Prod: SSO | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Giacomo Telesca |  | DEPLOY · Testing Prod: SSO | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Manuel |  | DEPLOY · Testing Prod: Stammdaten | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Giacomo Telesca |  | DEPLOY · Testing Prod: Stammdaten | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Manuel |  | DEPLOY · Testing Prod: DM | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Giacomo Telesca |  | DEPLOY · Testing Prod: DM | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Manuel |  | DEPLOY · Abnahme Prod: DM | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Giacomo Telesca |  | DEPLOY · Abnahme Prod: DM | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Manuel |  | RUN · Technischer Go Live DM | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Giacomo Telesca |  | RUN · Technischer Go Live DM | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Manuel |  | RUN · Initialload Dokumente | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Giacomo Telesca |  | RUN · Initialload Dokumente | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Manuel |  | RUN · Übergabe an Support | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Giacomo Telesca |  | RUN · Übergabe an Support | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Manuel |  | RUN · (Teil-)Projektabschluss | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32
UKG Implementation — HR Campus Demo | hr-campus-ukg-impl-demo-2026 | Giacomo Telesca |  | RUN · (Teil-)Projektabschluss | Hours | Allocation | Plan | Month | Merge |  |  |  | Medium | No | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18